## DF_R2_Super_Admin
Defect_Report_25.01.2025
# | Defect_id | Defect_Description | Tester Status | Developer Status | Priority | Remarks
| DF_CON_SA_002 | Edit Super Organization Page -> Warning Message is not displaying under the mandatory fields [ Organisation Name] if the fields data was cleared | Closed | Completed | P2
2 | DF_CON_SA_003 | Instead of "Edit Connfy Partner Shop" Page title --> It is displaying as Edit Shop Admin | Closed | Completed | P3
3 | DF_CON_SA_004 | Edit Connfy Partner Shop Page is displaying as "Entered Email already exists" after updating any details [Validation Issue] | Closed | Completed | P2
5 | DF_CON_SA_006 | Mandatory Symbols * is missing in Edit Connfy Partner Shop Page for the 'Email' | Closed | Completed | P3
8 | DF_CON_SA_009 | Start Date* & Until Date is Missing in Edit Connfy Partner Shop Page | Closed | Completed | P1
9 | DF_CON_SA_010 | Connfy partner Shop Admin Unable to log out Automatically after getting suspended from Super-Admin | Open | not fixed | P2
10 | DF_CON_SA_011 | In Connfy Partner shop Admin Page, If i select 'Cancel' for this alert "Are you want to suspend' Still it Deactivate the user and Vice Versa For Activate the user also | Closed | Completed | P1
11 | DF_CON_SA_012 | Are you sure you want to suspend-> Alert Modal message is showing instead of "Are you sure you want to Activate" for Activating the suspended user | Closed | Completed | P1 | Are you sure to suspend Shop Admin (user name) ?
13 | DF_CON_SA_014 | Page Title in the browser tab for 'Connfy Super Organization' page and 'Connfy Partner Shops' Page is showing us 'Shop Admin' | Closed | Completed | P2
14 | DF_CON_SA_015 | Validation occurs in Wifi "Settings" Modal Pop up Window for "Shop Home Page" & "Google Review Link" Page --> Remove Validation | Closed | Completed | P2
15 | DF_CON_SA_016 | In Wifi Setting Pop Up window -> Default text is showing in Wifi Name & Google Review Link fields | Closed | Completed | P2
16 | DF_CON_SA_017 | Back Navigation from Push Notification to Manage Shop is not working in side menu | Closed | Completed | P3 | Add shop name next to manage shop
| DF_CON_SA_018 | Integrity Violation PHP error for given duplicate shop name in connfy partner shop creation | closed | Completed | P1
|  | Special Characters allowed in shop name | closed | Completed |  | Give a tag line under the fields (donot use ex: @ in the shop name )
22 | DF_CON_SA_024 | Connfy Partner shop's Social Events Data is not displaying for Super Admin Social Events List page | closed | Completed | P2
Social Event Page
18 | DF_CON_SA_020 | Start date & End date is showing past date from calender in Edit Social Event Page | Open | not fixed | P3
19 | DF_CON_SA_021 | Start date & End date is not updated in Edit Social Event Page | Open | not fixed | P3
20 | DF_CON_SA_022 | Start Date & End date is able to select the same | Open | not fixed | P3
21 | DF_CON_SA_023 | Start date & End Date Format is showing as 'yyyy-mm-dd' in that particular field after date is picked from calender | Open | not fixed | P3